## 1A
Cluster | Lot | Solar Quote Accepted KVA | Installed Solar KVA | Export Limited to: | Installed PV Array KW | Installed Battery KWH | Solar Install Date | NMI Revenue meter install date | Droplet Install Date | SwitchDIn droplet installed | Jey Submitted
| 1A Min: 5kva - Max: Groupies: 5kva ¦ Cottage: 8.2kva ¦ Family: 10kva ¦ Comm Shed: 5kva | 23.2 | 101.4 | 94 | 120.92 |  |  |  |  | 16 | 76.4 | 92%
1A | 1 |  |  | 0 | [7 empty] | 100%
1A | 2 | 5 | 5 | 5 | 6.6 |  | 2025-01-20 | 2023-03-07 |  |  |  | 0%
1A | 3 |  |  | 0 |  |  |  | 2021-06-25 | 2024-10-01 | 1 |  | 92%
1A | 4 |  | 5 | 4.6 | 6.64 |  | 2023-10-19 | 2022-01-09 | 2023-10-31 | 1 | 5 | 92%
1A | 5 |  | 5 | 4.6 | 6.4 |  | 2022-12-14 | 2021-06-18 | 2023-10-11 | 1 | 5 | 91.46%
1A | 6 |  | 8.2 | 7.5 | 10.88 |  | 2022-12-09 | 2021-06-17 | 2023-10-13 | 1 | 8.2 | 0%
1A | 7 |  |  | 0 |  |  |  | 2021-06-17 |  |  |  | 92%
1A | 8 |  | 5 | 4.6 | 6.6 |  | 2024-10-02 | 2023-11-30 | 2024-10-03 | 1 |  | 0%
1A | 9 IEC did not install solar |  |  | 0 |  |  |  | 2021-06-07 |  |  |  | 92%
1A | 10 |  | 5 | 4.6 | 6.4 |  | 2022-08-29 | 2022-03-21 | 2024-02-17 | 1 | 5 | 100%
1A | 11 |  | 5 | 5 | 6.4 |  | 2022-08-30 | 2021-06-09 | 2023-11-30 | 1 | 5 | 0%
1A | 12 | 8.2 |  | 0 |  |  |  | 2024-09-20 |  |  |  | 92%
1A | 13 |  | 10 | 9.2 | 12.8 |  | 2022-08-23 | 2022-03-02 | 2023-05-11 | 1 | 10 | 92%
1A | 14 |  | 10 | 9.2 | 13.2 |  | 2024-10-29 | 2024-02-19 | 2025-01-17 | 1 |  | 0%
1A | 15 | 10 |  | 0 |  |  |  | 2021-06-25 |  |  |  | 92%
1A | 16 |  | 5 | 4.6 | 6.6 |  | 2024-01-25 | 2023-01-02 | 2024-02-07 | 1 |  | 91.46%
1A | 17 |  | 8.2 | 7.5 |  |  | 2023-10-17 | 2022-03-21 | 2023-10-25 | 1 | 8.2 | 0%
1A | 18 |  |  | 0 | [7 empty] | 92%
1A | 19 |  | 10 | 9.2 | 12.8 |  | 2022-09-01 | 2021-09-29 | 2023-05-10 | 1 | 10 | 92%
1A | 20 |  | 5 | 4.6 | 6.4 |  | 2022-12-09 | 2021-08-06 | 2023-07-11 | 1 | 5 | 92%
1A | 21 |  | 5 | 4.6 | 6.4 |  | 2023-02-13 | 2022-05-12 | 2023-05-09 | 1 | 5 | 92%
1A | 22 |  | 5 | 4.6 | 6.4 |  | 2022-12-08 | 2021-05-14 | 2023-05-09 | 1 | 5 | 92%
1A | 23 |  | 5 | 4.6 | 6.4 |  | 2022-12-02 | 2021-08-06 | 2023-07-01 | 1 | 5 | 0%
1A | 24 |  |  | 0 |  |  |  | 2024-07-26
Note on F2: Qi Jiang: Make sure total export is not over 95kW

## 1B
Limit %:
[14 empty] | 69% | 65%
Lot | System Owner | Block Type | Battery Allocation (kWh) | Inverter Model Installed | Max Export Capacity (kW) | Current Limited Exp kWh | Calc % | Updated Limited Exp kWh 241213 | Updated Limited Exp kWh 241217 | Updated Limited Exp kWh 250128 | Updated Limited Exp kWh 250201 | current | notes | Proposed Limited Export %
Lot 1 | Susan Gibson | Cottage | 9.5 | Symo 5.0 | 5 | 3 | 60% | 3.45 | 3.45 | 3.5 | 3.3 | 3.5 |  | 66%
Lot 2 | Karen Majer | Cottage | 9.5 | Symo 8.2 | 8.2 | 6.2 | 75.61% | 5.658 | 5.658 | 5.7 | 5.3 | 5.7 |  | 64.63%
Lot 3 | Sue Hardy | Cottage | 9.5 | Symo 5.0 | 5 | 3 | 60% | 3.45 | 3.45 | 3.5 | 3.3 | 3.5 |  | 66%
Lot 4 | Jennie McCormack | Cottage | 9.5 | Symo 5.0 | 5 | 5 | 100% | 3.45 | 3.45 | 3.5 | 3.5 | 3.5 | 3.65 offline an hour | 70%
Lot 5 | Michael Sorensen | Cottage | 9.5 | Symo 8.2 | 8.2 | 6.2 | 75.61% | 5.658 | 5.658 | 5.7 | 5.3 | 5.7 |  | 64.63%
Lot 6 | Toni Aslett | Cottage | 9.5 | Symo 8.2 | 8.2 | 6.2 | 75.61% | 5.658 | 5.658 | 5.7 | 5.3 | 5.7 |  | 64.63%
Lot 7 | Bridget Bolitho | Cottage | 9.5 | Symo 5.0 | 5 | 3 | 60% | 3.45 | 3.45 | 3.5 | 3.3 | 3.5 |  | 66%
Lot 8 | Hamish Jolly | Family | 13.5 | Symo 6.0 | 6 | 4.5 | 75% | 4.14 | 4.14 | 4.1 | 3.9 | 4.1 |  | 65%
Lot 9 | Phillip Crockford | Family | 13.5 | Symo 10.0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Lot 10 | Jennifer Widmer | Family | 13.5 | Symo 5.0 | 5 | 3.5 | 70% | 3.45 | 3.45 | 3.5 | 3.3 | 3.5 | 3.65 offline 18 mins | 66%
Lot 11 | Hannah Flack | Family | 13.5 | Symo 6.0 | 6 | 3 | 50% | 4.14 | 4.14 | 4.1 | 3.9 | 4.1 |  | 65%
Lot 12 | Paul Wilkinson | Family | 13.5 | Symo 10.0 | 10 | 8 | 80% | 6.9 | 6.9 | 6.9 | 6.5 | 6.9 |  | 65%
Lot 13 | Stephen Hall | Family | 13.5 | Symo 10.0 | 10 | 8 | 80% | 6.9 | 6.9 | 6.9 | 6.5 | 6.9 |  | 65%
Lot 14 | Craig Headford | Family | 13.5 | Symo 10.0 | 10 | 8 | 80% | 6.9 | 6.9 | 6.9 | 6.5 | 6.9 |  | 65%
Lot 15 | Jema McCabe | Groupie | 6 | Symo 5.0 | 5 | 3.5 | 70% | 3.45 | 3.45 | 3.5 | 3.3 | 3.5 |  | 66%
Lot 16 | Colin Dear | Groupie | 6 | Symo 5.0 | 5 | 3 | 60% | 3.45 | 3.45 | 3.5 | 3.3 | 3.5 |  | 66%
Lot 17 | Candice Papalia | Groupie | 6 | Symo 5.0 | 5 | 3.5 | 70% | 3.45 | 3.45 | 3.5 | 3.3 | 3.5 |  | 66%
Lot 18 | Chloe Adam | Groupie | 6 | Symo 5.0 | 5 | 5 | 100% | 0 | 3.45 | 3.5 | 3.3 | 3.5 |  | 66%
Lot 19 | Alex Jolly | Groupie | 6 | Symo 5.0 | 5 | 3 | 60% | 3 | 3.45 | 3.5 | 3.3 | 3.5 |  | 66%
Lot 20 | Nathan Stone | Family | 13.5 | Symo 10.0 | 10 | 8 | 80% | 6.9 | 6.9 | 6.9 | 6.5 | 6.9 |  | 65%
Lot 21 | Nicholas Mead | Fam ily | 13.5 | Symo 10.0 | 10 | 8 | 80% | 8 | 6.9 | 6.9 | 6.9 | 6.9 | 7.3 offline 18 hours | 69%
Common |  |  | 14 | [5 empty] | 0 | 0 | 0 | 0
|  |  | 232 |  | 136.6 | 101.6 |  | 91.454 | 94.254 | 94.8 | 89.8 | 94.8
Note on D5: Craig: Updated based on MH email 16/8/24 in Google Drive (battery bulletin)
Note on G5: Craig: Info from Bodhi 9 Sep 2024 (Email)
Note on B14: Not yet installed
Note on B23: Installed Nov 2024 - Awaiting droplet

## 1C
- | Cluster | Lot | Solar Quote Accepted KVA | Installed Solar KVA | Export Limited to: | Installed PV Array KW | Installed Battery KWH | Solar Install Date | NMI Revenue meter install date | Droplet Install Date | SwitchDIn droplet installed | Jey Submitted
81 |  | 1C Min: 5kva - Max: Groupies: 5kva ¦ Cottage: 10kva ¦ Family: 15kva ¦ Comm Shed: 5kva | 20 | 112.8 | 96.4 | 141.85 |  |  |  |  | 15 | 109.6 | 84%
82 | 1C | 1 |  | 8.2 | 6.9 | 10.88 |  | 2022-07-06 | 2021-05-20 | 2023-02-22 | 1 | 8.2 | 84.15%
83 | 1C | 2 |  | 5 | 4.2 | 6.64 |  | 2023-02-10 | 2021-05-14 | 2023-05-11 | 1 | 5 | 84%
84 | 1C | 3 - Brendan Kelly Inst |  | 8.2 | 6.9 | 0 |  |  | 2021-12-09 | 2024-01-31 | 1 | 5 | 84.15%
85 | 1C | 4 - Brendan Kelly Inst |  | 5 | 4.2 | 0 |  |  | 2022-01-09 | 2024-02-02 | 1 | 5 | 84%
86 | 1C | 5 - Offline 19/09/24 |  | 8.2 | 6.9 | 10.88 |  | 2022-07-13 | 2021-06-17 | 2023-05-29 | 1 | 8.2 | 84.15%
87 | 1C | 6 |  | 10 | 10 | 12.45 |  | 2023-10-16 | 2022-07-04 | 2023-10-30 | 1 | 10 | 100%
88 | 1C | 7 - Dex E (Waiting on Tate/Not Running/No Droplet Yet) |  | 0 | 0 | 13.28 |  | 2023-10-27 | 2021-12-17 |  |  | 15 | 0%
89 | 1C | 8 |  | 10 | 8.4 | 12.8 |  | 2022-06-28 | 2021-06-07 | 2024-01-30 | 1 | 10 | 84%
90 | 1C | 9 | 15 |  | 0 |  |  |  | 2024-08-29 |  |  |  | 0%
91 | 1C | 10 |  | 5 | 4.2 | 6.64 |  | 2022-11-29 | 2021-05-14 | 2023-09-04 | 1 | 5 | 84%
92 | 1C | 11 | 5 |  | 0 |  |  |  | 2024-05-27 |  |  |  | 0%
93 | 1C | 12 |  | 5 | 4.2 | 6.64 |  | 2023-10-17 | 2022-04-08 | 2024-02-02 | 1 |  | 84%
94 | 1C | 13 |  | 5 | 4.2 | 6.4 |  | 2022-12-06 | 2021-08-06 | 2024-02-07 | 1 | 5 | 84%
95 | 1C | 14 |  | 5 | 4.2 | 6.4 |  | 2022-12-02 | 2021-08-04 | 2023-05-29 | 1 | 5 | 84%
96 | 1C | 15 |  | 8.2 | 6.9 | 9.96 |  | 2023-10-18 | 2021-07-16 | 2023-10-30 | 1 | 8.2 | 84.15%
97 | 1C | 16 |  | 10 | 8.4 | 13.28 |  | 2023-09-11 | 2021-07-16 | 2023-10-10 | 1 | 10 | 84%
98 | 1C | 17 |  |  | 0 |  |  |  | 2023-12-05 |  |  |  | 0%
99 | 1C | 18 - (Waiting on PQA/Not Running/Export Limit has been updated to 8.86kW on 14/01/2025) |  | 10 | 8.4 | 12.32 |  | 2024-07-16 | 2022-04-08 | 2024-07-17 | 1 |  | 84%
100 | 1C | 19 |  | 10 | 8.4 | 13.28 |  | 2023-03-03 | 2022-03-02 | 2023-05-11 | 1 | 10 | 84%

## 2A
- | Cluster | Lot | Solar Quote Accepted KVA | Installed Solar KVA | Export Limited to: | Installed PV Array KW | Installed Battery KWH | Solar Install Date | NMI Revenue meter install date | Droplet Install Date | SwitchDIn droplet installed | Jey Submitted
102 |  | 2A Min: 5kva - Max: Groupies: 5kva ¦ Cottage: 8.2kva ¦ Family: 12.5kva ¦ Comm Shed: 5kva | 8.2 | 74.6 |  | 91.59 |  |  |  |  | 10 | 0
103 | 2A | 1 | 8.2 | [5 empty] | 2024-08-13
104 | 2A | 2 |  | 8.2 |  | 10.79 |  | 2023-03-22 | 2022-07-04 | 2023-09-11 | 1
105 | 2A | 3
106 | 2A | 4
107 | 2A | 5 |  | 8.2 |  | 10.75 |  | 2023-12-21 | 2022-09-05 | 2024-02-12 | 1
108 | 2A | 6 - IEC did NOT install |  | 5 |  | 0
109 | 2A | 7
110 | 2A | 8
111 | 2A | 9 - IEC did not install solar or droplet. | [6 empty] | 2023-02-14
112 | 2A | 10
113 | 2A | 11
114 | 2A | 12 |  | 10 |  | 12.86 |  | 2023-11-02 | 2022-07-04 | 2023-11-30 | 1
115 | 2A | 13 |  | 8.2 |  | 10.79 |  | 2024-02-22 | 2022-03-14 | 2024-03-06 | 1
116 | 2A | 14 |  | 5 |  | 6.64 |  | 2023-12-18 | 2022-04-08 | 2024-05-01 | 1
117 | 2A | 15 |  | 5 |  | 6.6 |  | 2024-02-28 | 2023-02-06 | 2024-05-21 | 1
118 | 2A | 16
119 | 2A | 17 |  | 5 |  | 6.64 |  | 2023-11-09 | 2022-09-05 | 2024-02-22 | 1
120 | 2A | 18 |  | 5 |  | 6.64 |  | 2023-11-14 | 2022-09-05 | 2023-12-01 | 1
121 | 2A | 19 |  | 5 |  | 6.6 |  | 2024-08-16 | 2022-05-20 | 2024-09-12 | 1
122 | 2A | 20
123 | 2A | 21 |  | 10 |  | 13.28 |  | 2023-02-01 | 2022-01-09 | 2023-09-11 | 1
124 | 2A | 22
125 | 2A | 23
126

## 2B
- | Cluster | Lot | Solar Quote Accepted KVA | Installed Solar KVA | Export Limited to: | Installed PV Array KW | Installed Battery KWH | Solar Install Date | NMI Revenue meter install date | Droplet Install Date | SwitchDIn droplet installed | Jey Submitted | proposed % | actual %
127 |  | 2B Min: 5kva - Max: Groupies: 5kva ¦ Cottage: 8.2kva ¦ Family: 12.5kva ¦ Comm Shed: 5kva | 22.5 | 113.5 | 96.4 | 116.48 |  |  |  |  | 14 | 0 | 81% | 80.49%
128 | 2B | 1 |  | 8.2 | 6.6 | 10.56 |  | 2024-02-26 | 2021-05-10 | 2024-08-07 | 1 |  | 81% | 80.49%
129 | 2B | 2 |  | 8.2 | 6.6 | 10.79 |  | 2024-10-11 | 2022-04-27 | 2024-02-14 | 1 |  | 81% | 82%
130 | 2B | 3 |  | 5 | 4.1 | 6.64 |  | 2023-01-20 | 2021-05-10 | 2024-04-08 | 1 |  | 81% | 82%
131 | 2B | 4 | 5 | 5 | 4.1 |  |  |  | 2024-06-25 |  |  |  | 81% | 80.49%
132 | 2B | 5 |  | 8.2 | 6.6 | 10.79 |  | 2022-12-19 | 2021-05-10 | 2023-10-11 | 1 |  | 81% | 100%
133 | 2B | 6 |  | 5 | 5 | 6.57 |  | 2023-10-23 | 2023-09-08 | 2024-05-01 | 1 |  | 81% | 82%
134 | 2B | 7 |  | 5 | 4.1 | 6.4 |  | 2022-09-02 | 2021-05-10 | 2023-05-08 | 1 |  | 81% | 82%
135 | 2B | 8 |  | 5 | 4.1 | 6.16 |  | 2024-06-04 | 2022-09-05 | 2023-05-08 | 1 |  | 81% | 80.49%
136 | 2B | 9 |  | 8.2 | 6.6 | 9.89 |  | 2023-12-06 | 2022-09-05 | 2024-02-15 | 1 |  | 81% | 80.49%
137 | 2B | 10 - IEC did not install. Brendan Kelly (panels are installed). // Found data for inverter since March 2024, Jennie-E47 |  | 8.2 | 6.6 |  |  |  | 2023-03-02 | 2024-03-25 | 1 |  | 81%
138 | 2B | 11 |  |  | 0 | [7 empty] | 81% | 82%
139 | 2B | 12 |  | 5 | 4.1 | 6.6 |  | 2024-09-18 | 2024-03-05 |  |  |  | 81% | 100%
140 | 2B | 13 | 5 | 5 | 5 | 6.6 |  | 2025-01-06 | 2024-09-25 | 2025-01-16 | 1 |  | 81%
141 | 2B | 14 |  |  | 0 | [7 empty] | 81% | 82%
142 | 2B | 15 |  | 5 | 4.1 | 6.6 |  | 2024-05-22 | 2023-01-19 | 2024-09-16 | 1 |  | 81% | 82%
143 | 2B | 16 |  | 5 | 4.1 | 6.4 |  | 2022-09-01 | 2022-03-02 | 2023-07-12 | 1 |  | 81% | 82%
144 | 2B | 17 |  | 5 | 4.1 | 6.64 |  | 2023-12-04 | 2022-03-14 | 2024-02-14 | 1 |  | 81%
145 | 2B | 18 |  |  | 0 | [7 empty] | 81%
146 | 2B | 19 |  |  | 0 |  |  |  | 2024-09-30 |  |  |  | 81% | 100%
147 | 2B | 20 | 12.5 | 12.5 | 12.5 | 15.84 |  | 2025-01-16 | 2022-10-19 |  |  |  | 81% | 81%
148 | 2B | 21 |  | 10 | 8.1 |  |  | 2022-12-20 | 2021-10-05 | 2023-05-09 | 1 |  | 81%
149 | 2B | 22
17

## 3A
- | Cluster | Lot | Solar Quote Accepted KVA | Installed Solar KVA | Export Limited to: | Installed PV Array KW | Installed Battery KWH | Solar Install Date | NMI Revenue meter install date | Droplet Install Date | SwitchDIn droplet installed | Jey Submitted
151 |  | 3A Min: 5kva - Max: Groupies: 5kva ¦ Cottage: 8.2kva ¦ Family: 8.2kva ¦ Comm Shed: 5kva | 34.6 | 56.4 |  | 67.1 |  |  |  |  | 6
152 | 3A | 1 | [6 empty] | 2024-02-27
153 | 3A | 2
154 | 3A | 3
155 | 3A | 4 |  | 5 |  |  |  | 2023-05-19 | 2022-10-14 | 2023-08-18 | 1
156 | 3A | 5
157 | 3A | 6
158 | 3A | 7 |  | 5 |  | 6.6 |  | 2024-02-15 | 2023-03-02 | 2024-04-08 | 1
| 3A | 8
159 | 3A | 9 | 8.2 | 8.2 |  | 10.56 |  | 2025-01-08 | 2023-08-21
160 | 3A | 10 | [6 empty] | 2024-03-12
161 | 3A | 11 | 8.2 | [5 empty] | 2024-05-27
162 | 3A | 12 | 8.2 | [5 empty] | 2024-02-28
163 | 3A | 13
164 | 3A | 14
165 | 3A | 15 IEC did prewire client not responding, IEC did not install | 5 | [5 empty] | 2022-08-12
166 | 3A | 16 |  | 5 |  | 6.6 |  | 2024-07-30 | 2022-09-28
167 | 3A | 17
168 | 3A | 18 IEC not installing. | [6 empty] | 2023-11-29
169 | 3A | 19 |  | 5 |  | 6.64 |  | 2023-05-12 | 2022-09-28 | 2023-08-18 | 1
170 | 3A | 20 | 5 | [5 empty] | 2024-10-16
171 | 3A | 21
172 | 3A | 22 |  | 5 |  | 6.6 |  | 2024-05-21 | 2023-08-21 | 2024-09-16 | 1
173 | 3A | 23
174 | 3A | 24 |  | 10 |  | 12.9 |  | 2023-12-14 | 2023-04-04 | 2024-02-15 | 1
175 | 3A | 25 |  | 5 |  | 6.64 |  | 2023-10-12 | 2022-11-09 | 2023-12-01 | 1
176 | 3A | 26
177 | 3A | 27 | 8.2 | 8.2 |  | 10.56 |  | 2024-12-19 | 2024-06-25
56.4

## 3B
- | Cluster | Lot | Solar Quote Accepted KVA | Installed Solar KVA | Export Limited to: | Installed PV Array KW | Installed Battery KWH | Solar Install Date | NMI Revenue meter install date | Droplet Install Date | SwitchDIn droplet installed | Jey Submitted
179 |  | 3B Min: 5kva - Max: Groupies: 5kva ¦ Cottage: 10kva ¦ Family: 15kva ¦ Comm Shed: 5kva | 10 | 64.6 |  | 66.48 |  |  |  |  | 3 | 0
180 | 3B | 1
181 | 3B | 2 |  | 8.2 |  | 10.56 |  | 2024-10-15 | 2023-04-19
182 | 3B | 3
183 | 3B | 4
184 | 3B | 5 |  | 8.2 |  |  |  |  | 2022-12-20 |  | 1
185 | 3B | 6 |  | 8.2 |  | 10.56 |  | 2024-09-17 | 2024-02-02
186 | 3B | 7 |  | 5 |  |  |  |  | 2023-06-28 | 2024-02-15 | 1
187 | 3B | 8 |  | 10 |  | 12.32 |  | 2024-07-17 | 2023-09-12 | 2024-07-18 | 1
188 | 3B | 9
189 | 3B | 10 |  | 10 |  | 13.2 |  | 2024-10-15 | 2024-02-09
190 | 3B | 11
191 | 3B | 12
192 | 3B | 13 |  | 10 |  | 13.2 |  | 2024-10-21 | 2024-02-21
193 | 3B | 14 | [6 empty] | 2024-10-03
194 | 3B | 15 | 5 | [5 empty] | 2025-01-20
195 | 3B | 16
196 | 3B | 17
197 | 3B | 18 | 5 | [5 empty] | 2024-02-21
198 | 3B | 19 |  | 5 |  | 6.64 |  | 2024-09-25 | 2024-01-10